## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
| Landing Page | Public | Simple | Public site locker-drone.tech: product introduction, services, FAQ, links to app and policy pages | Iteration 1 | Done
| Splash & Onboarding | Common | Simple | Mobile: splash checks saved token and routes by role; onboarding slides; location permission request | Iteration 1 | Done
| User Register | Common | Medium | Register with full name, email, phone, password, or Google / phone OTP (Firebase); first phone login asks for full name (Complete registration); creates CUSTOMER account | Iteration 1 | Done
| User Login | Common | Medium | Login by email + password, Google, phone + Firebase OTP (Firebase ID token verified on server) or email OTP; app routes to Customer / Locker Technician / Drone Technician home by role, ADMIN is told to use the web | Iteration 1 | Done
| Reset Password | Common | Simple | Forgot password: receive OTP by email, verify, set new password | Iteration 1 | Done
| Admin Login (2FA) | Common | Simple | Web admin: email + password, then 6-digit OTP sent by email (max 5 wrong attempts); Lock.R branded login page | Iteration 1 | Done
| User Profile | Common | Medium | View/edit profile, avatar upload (Cloudinary signed direct upload), change password, bank account used for refunds | Iteration 1 | Done
| Notifications | Common | Medium | Push (FCM) + in-app list for order status, pickup code, ticket assigned, schedule due, refund, feedback; branded emails for drone orders; tap opens the right screen by role; delete one / all; Vietnamese content | Iteration 2 | Done
| Kiosk QR Login | Common | Medium | Kiosk shows a login QR (expires after 2 minutes); customer scans it in the app and confirms; email OTP on kiosk as alternative | Iteration 3 | Done
| Face Registration / Face Login | Common | Complex | Register and log in by face. Hidden by feature flag: backend AI service does not exist | Iteration 4 | Deferred
| Service Plans (Subscription) | Common | Medium | Customer service plans / pricing packages. Hidden by feature flag: no backend endpoints | Iteration 4 | Deferred
| Home Page | Customer | Medium | Customer home: quick actions (Send parcel, Rent locker, Drone delivery, QR scan), nearby lockers, active orders, wallet balance | Iteration 1 | Done
| Stores List & Store Details | Customer | Medium | List stores with lockers, search, favorites, store details, lockers of a store, directions to the exact locker GPS position | Iteration 1 | Done
| Locker Map | Customer | Medium | Map of lockers with online / offline status; offline or MAINTENANCE lockers cannot be booked | Iteration 1 | Done
| Locker Layout (Box Map) | Customer | Medium | Real box layout of a locker (STANDARD, XL, DRONE), free / reserved / occupied / fault state; tap an empty box to book | Iteration 1 | Done
| Send Parcel | Locker Send | Complex | Choose locker, box size or box on the map, receiver phone / name / email, voucher, loyalty points -> create SEND order, box RESERVED with hold time; unpaid order auto-cancelled and box released | Iteration 1 | Done
| Drop Parcel | Locker Send | Medium | Open the box from the app or by send code on kiosk, put the parcel in, close the door, confirm 'Dropped' -> box OCCUPIED, order STORING | Iteration 1 | Done
| Share Pickup Code | Locker Send | Medium | Sender shares pickup PIN/QR (Zalo / Messenger / SMS); system sends code to receiver by email and SMS (eSMS.vn / Twilio) | Iteration 3 | Done
| Change Pickup PIN | Locker Send | Simple | Sender regenerates the pickup PIN if the code was leaked; old PIN stops working | Iteration 3 | Done
| Incoming Orders (Receiver) | Locker Send | Medium | Receiver with an account (same phone or recipient email) sees 'Waiting for pickup' tab with PIN, filters by time / location, receiver order detail page | Iteration 3 | Done
| Delegated Pickup | Locker Send | Medium | Owner of a STORING order delegates pickup to another phone; PIN is regenerated, delegate sees the order in 'Delegated orders' and opens the box from kiosk or app | Iteration 3 | Done
| BLE Proximity Unlock | Locker Send | Complex | App detects the BLE beacon broadcast by the locker Pi (CAB-TU01) and opens the box in one tap; alternatives: QR scan, kiosk PIN | Iteration 2 | Done
| Rent Locker | Locker Rental | Complex | Choose locker, box type, number of hours -> pay -> open box -> start rental; reopen many times during rental, extend rental (pay the difference), end rental & take items | Iteration 1 | Done
| Overdue Fee | Locker Rental | Medium | Overdue pickup / rental must pay overtime fee (by rental price) before the box opens on app or kiosk; grace period and overdue release configurable by admin | Iteration 3 | Done
| My Orders & Order Details | Customer | Medium | List orders by status; detail with status history, locker location, each payment with method and transaction id, receiver info, box relocation record | Iteration 1 | Done
| Payment (SePay VietQR) | Payment | Complex | Checkout by bank transfer: server generates VietQR with order code in transfer content, app opens bank app prefilled; SePay webhook marks PAID only when full amount received; MoMo / VNPay / cash removed | Iteration 3 | Done
| Payment Simulator (Test Mode) | Payment | Simple | Button on the VietQR screen to simulate a successful transfer, only when admin turns test mode on | Iteration 3 | Done
| Refund Request | Payment | Medium | Customer requests refund for a paid order with evidence photos; cancelled / failed orders go to REFUND_PENDING; status, proof and filters in 'Refund requests' | Iteration 2 | Done
| Rating & Feedback | Customer | Simple | Rate completed order (stars + comment) or send a complaint; receive admin reply as notification | Iteration 3 | Done
| Create Incident Report & My Reports | Customer | Medium | Report a faulty box / locker (locker, box, title, description, photos) -> box FAULT, ticket OPEN; tabs and filters to follow progress, rate the technician | Iteration 2 | Done
| Wallet Top-up | Wallet | Medium | Top up wallet by VietQR; balance is credited only after SePay webhook confirms | Iteration 2 | Done
| Withdraw & Withdrawal Requests | Wallet | Medium | Withdraw to bank account (>= 10,000 VND), wallet debited immediately, request 'Pending' until admin approves or rejects | Iteration 1 | Done
| Transactions History | Wallet | Simple | Wallet transactions (top-up, payment, refund, withdrawal, points reversal) with spending statistics by payment method | Iteration 2 | Done
| Promotions & My Vouchers | Promotion | Medium | View active promotions, save vouchers, apply at checkout; vouchers can be system-wide or tied to one locker ('Offers at this locker') | Iteration 3 | Done
| Loyalty Points | Promotion | Medium | Earn points on completed paid orders (default 1 point / 1,000 VND), tiers Bronze -> Platinum by total earned points, history; pay orders with points; points reversed on refund | Iteration 3 | Done
| Drone Booking | Drone Delivery | Complex | Choose receiver locker and receive box (has landing pad, free DRONE box, <= 5 km), parcel type, weight level, declared value, fragile, receiver; prohibited goods commitment; fee by weight -> create order and pay | Iteration 2 | Done
| Drone Home Pickup | Drone Delivery | Complex | Customer books a drone pickup at a chosen location; technician is dispatched, must take a parcel photo when confirming pickup; delivery failure handling | Iteration 3 | Done
| Drone Delivery Tracking | Drone Delivery | Complex | Timeline of stages (awaiting dispatch -> departed -> en route -> arrived -> ready for pickup) with time per stage, pickup photo, receiver locker and box, A -> B map, cancel while awaiting dispatch, surcharge banner | Iteration 2 | Done
| Drone Live Map | Drone Delivery | Medium | Live drone position over STOMP (/topic/deliveries/{orderId}/position); DEMO orders interpolated, real drones from telemetry | Iteration 2 | Done
| Drone Dispatch | Drone Technician | Complex | Dispatch tab: accept paid order whose parcel is dropped, choose an idle drone with enough battery -> mission created, drone RESERVED (locked against double accept) | Iteration 1 | Done
| Loading Confirmation | Drone Technician | Medium | Weigh parcel, system-generated seal code, 3-item checklist; weight over tolerance (50 g) -> fee recalculated, customer pays surcharge or declines | Iteration 1 | Done
| Launch & Flight Stages | Drone Technician | Complex | Launch within flight hours (not paused by admin), re-check battery / pad; DEMO stages automatic; STANDARD stages pushed by real telemetry or confirmed by dispatcher. Not yet tested with a real flight | Iteration 4 | Doing
| Cancel / Flight Failure | Drone Technician | Medium | Cancel before launch or report failed flight with reason; drone -> FAULT + drone ticket; order -> REFUND_PENDING; mission record kept; unpaid / undispatched orders auto-cancelled | Iteration 2 | Done
| Drone Fleet (Mobile) | Drone Technician | Medium | Claim a drone, change status (Ready / Charging / Maintenance / Fault with reason), update battery, maintenance log, drone tickets | Iteration 2 | Done
| Technician Shift & Presence | Drone Technician | Simple | Technician starts / ends shift on the app (shift card); admin sees who is on duty | Iteration 3 | Done
| Flight Data & Drone Camera | Drone Technician | Complex | Pi on drone reads MAVLink (Pixhawk 6C) and sends signed telemetry over MQTT; MJPEG camera stream; Flight Data screen with safety lock. Bench-tested only | Iteration 4 | Doing
| Parcel Drop Incident | Drone Delivery | Complex | Report dropped parcel -> delivery stopped; admin assigns recovery, verifies evidence, decides free redelivery / compensation refund; customer accepts or asks review | Iteration 3 | Done
| Technician Home (Tickets) | Locker Technician | Complex | Ticket queue and 'My tasks': claim -> IN_PROGRESS, progress log + photos; resolve by relocate to new box / hand over (customer PIN) / seal to hub / fix on site / lock box; after-fix photo required; occupied boxes protected | Iteration 1 | Done
| Technician Profile | Locker Technician | Simple | Technician profile, edit info, performance and SLA statistics | Iteration 1 | Done
| SLA Extension & Return Ticket | Locker Technician | Simple | Extend SLA only while holding the ticket (max 2 x 24 h, reason required); return ticket to queue with reason | Iteration 1 | Done
| Periodic Inspection | Locker Technician | Medium | Scheduled checklist per locker / drone: Pass / Fail per item with photos; failed item opens a ticket automatically | Iteration 1 | Done
| Emergency Open (Master) | Locker Technician | Medium | Open a box with master command, reason required; result opened / timeout / error / jammed; jammed -> box marked fault + ticket | Iteration 3 | Done
| IoT Devices | Locker Technician | Medium | Devices of assigned lockers, last seen, restart controller command, mark device faulty | Iteration 3 | Done
| Parcel Recovery | Locker Technician | Medium | Recovery queue for dropped drone parcels: accept task, GPS check-in, directions, evidence photos, submit to admin, hand over to hub (still uses mock data in part of the flow) | Iteration 3 | Doing
| Admin Dashboard | Admin | Medium | Revenue, orders by status, peak hours, user growth, top locations (real data) | Iteration 1 | Done
| Users List & User Details | Admin | Medium | Search users, create staff (Locker / Drone Technician), lock account, delete user (frees email / phone). Role change UI not built yet | Iteration 2 | Doing
| Stores Management | Admin | Simple | CRUD stores, store photos, address and map position | Iteration 1 | Done
| Lockers & Locker Layout | Admin | Complex | CRUD lockers, batch create / delete boxes, box map, exact GPS picker, box QR printing, assign responsible technician, assign Pi controller by MAC, test-open boxes, IoT connection logs | Iteration 2 | Done
| Drones Management | Admin | Medium | Add drone, assign station locker and technician, change status / battery via admin route; drone hardware (device) assignment, drone IoT logs page | Iteration 3 | Done
| Drone Orders | Admin | Medium | List and detail of drone orders: mission record, timeline, pickup photo, Leaflet map, home pickup assignment, report failed flight | Iteration 2 | Done
| Drone Incidents | Admin | Medium | Parcel drop incidents: assign technician, verify result, free redelivery or compensation refund, close | Iteration 3 | Done
| Orders Management | Admin | Medium | Search orders, order detail, status history, linked maintenance reports and refunds; Vietnam time | Iteration 1 | Done
| Payments, Refunds & Withdrawals | Admin | Medium | Payment search / detail / statistics; approve refund by bank transfer with receipt or reject with reason; approve / reject withdrawals | Iteration 2 | Done
| Revenue Report | Admin | Medium | Revenue by real collected money, by service / locker / period | Iteration 1 | Done
| Promotions & Loyalty | Admin | Medium | Create promotions (code, % or amount, period, usage limit, locker scope); loyalty rules | Iteration 3 | Done
| Maintenance (Tickets, Schedules, Technicians) | Admin | Complex | Ticket list with SLA, assign / reassign, batch delete; inspection schedules; technicians page with assignments and ranking | Iteration 2 | Done
| Feedback | Admin | Medium | Service ratings, reply to customer, mark handled, statistics by day / week / month, NPS | Iteration 3 | Done
| Notifications (Broadcast) | Admin | Simple | Send notification / broadcast to users, notification statistics | Iteration 1 | Done
| Business Settings | Admin | Complex | Configurable rules per service (system_settings): prices, payment methods, unpaid auto-cancel, pickup deadline / grace time / overdue release, drone limits and battery threshold, refund deadline, SLA extensions | Iteration 1 | Done
| Services Management | Admin | Simple | One card per service (send, rental, drone) with price, editable rules and period performance | Iteration 1 | Done
| Scheduled Jobs | Admin | Simple | View scheduled jobs (auto-cancel unpaid, pickup reminder, overdue to warehouse, box reconciliation) and 'Run now' | Iteration 2 | Done
| Knowledge Base | Admin | Medium | Upload PDF / DOCX / MD, choose allowed roles, view original file and chunks, conversations, run retrieval evaluation | Iteration 1 | Done
| AI Assistant Chat & History | AI Assistant | Complex | Answers with citations only from documents the role may read, refuses out-of-scope; answers about the asker's real orders; understands Vietnamese without diacritics | Iteration 1 | Done
| Kiosk Pickup (PIN / QR) | Kiosk | Medium | Receiver without account enters PIN or scans QR -> box opens -> order completed, box released; detailed message on wrong PIN and lock after 5 wrong attempts | Iteration 1 | Done
| Kiosk Rent & Drop | Kiosk | Complex | Login (email OTP / QR / quick register), choose box on real layout, hours, voucher -> pay VietQR -> box opens; rental code to continue or end rental; on-screen keyboard | Iteration 2 | Done
| Pi Service Panel (/service) | IoT | Medium | Technician panel on the Pi: open each box with custom pulse time, 40-pin map of current config | Iteration 3 | Done
| Cabinet Controller (GPIO + MQTT) | IoT | Complex | Pi drives relays, lock signals, door sensors, TB6600 sliding lid by GPIO; MQTT topic cabinet/{lockerId}, open command with boxId + slotIndex; restart command. 7 boxes open on CAB-TU01, door sensors and axis 2 not finished | Iteration 2 | Doing
| Private MQTT Broker | IoT | Medium | Mosquitto with one account per Pi, ACL per locker, wss through Nginx (code deployed, not enabled on VM) | Iteration 4 | Pending
| IoT Health Monitoring | IoT | Medium | Controller without heartbeat is logged as disconnected (done); still missing: device OFFLINE state, fault / jammed result -> box fault + ticket, alert to admin | Iteration 4 | Doing
| Role-based Authorization Hardening | Common | Complex | Owner + role checks inside services (SEC-03, SEC-05, SEC-06). Done: /api/users/** owner-or-admin, notifications by owner | Iteration 4 | Doing
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple | <=7 fields | <=3 transactions
| medium | <=15 fields | <= 7 transactions
| complex | >15 fields | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions
Planned iterations:
Iteration 1: 13/09/2026 - 26/09/2026 ¦ Iteration 2: 27/09/2026 - 10/10/2026 ¦ Iteration 3: 11/10/2026 - 24/10/2026 ¦ Iteration 4: 25/10/2026 - 07/11/2026
Status as of 21/10/2026: Done = merged to main and on production; Doing = coded / PR open / waiting deploy; Pending = not started; Deferred = hidden behind feature flag, backend not available

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
| SEC-01: Production JWT secret was a hardcoded default value | Anyone who knows the default string can forge an ADMIN token | High | huynqbse180211 | 2026-09-13 |  | Open | Compose now requires APP_SECURITY_JWT_SECRET from .env (backend #10); close after the secret on the VM is rotated (all users logged out)
| SEC-02: Any user could make themselves ADMIN via PUT /api/users/{id} | Customer gets admin web access | High | huynqbse180211 | 2026-09-13 | 2026-10-11 | Closed | roles/status removed from non-admin request (backend #54); owner-or-admin + inactive token block (backend #55)
| SEC-03: Order / payment status can be changed without control | Complete or cancel other people's orders, mark self as paid | High | viltyse182544 | 2026-09-13 |  | Open | PATCH /api/orders/{id}/status, POST /api/orders/{id}/checkout, PATCH /api/payments/{id}/status still accept any JWT
| SEC-04: MQTT uses a public broker without auth or TLS | Anyone can publish an open command to a locker | High | huynqbse180211 | 2026-09-13 |  | Open | Private Mosquitto broker merged and deployed 27/09 but not enabled on VM; Pi .env must be switched
| SEC-05: Pickup PIN can leak through other users' data | Attacker reads PIN and opens another customer's box | High | viltyse182544 | 2026-09-13 |  | Open | Notifications now owner-only; order responses still carry pinCode - needs owner check
| SEC-06: Anyone can fake IoT device / box status | Mass-lock boxes, fake device online / offline | Medium | nhatkse182290 | 2026-09-13 |  | Open | POST /api/iot/device-status and /api/iot/box-status accept any JWT
| SEC-07: Email OTP written to log in plain text | Anyone reading logs can log in | High | huynqbse180211 | 2026-09-13 | 2026-09-16 | Closed | Removed from log, email masked (backend #10), deployed 16/09
| SEC-08: Cloudflare API token pasted into chat history | Whoever has the chat can overwrite admin web, landing, mobile web | High | huynqbse180211 | 2026-09-16 |  | Open | Create new token, reload GitHub secrets, delete old token
| SEC-09: Phone login accepted unverified phone numbers | Log in as any phone number | High | huynqbse180211 | 2026-10-12 | 2026-10-13 | Closed | Only verified Firebase ID token accepted, complete-registration requires tempToken (backend #59)
| GitHub Actions quota exhausted (2,000 / 2,000 minutes) | All CI and deploy jobs fail after 2-5 seconds | High | huynqbse180211 | 2026-09-15 | 2026-09-16 | Closed | Repos switched to public -> free Actions
| Old Azure subscription ran out of credit | Production down | High | huynqbse180211 | 2026-10-03 | 2026-10-04 | Closed | Moved to new VM (Malaysia West), copied 9 DBs + assistant-db
| Backend deploy failed 11 times on the new VM | No backend release reaches production | High | huynqbse180211 | 2026-10-05 | 2026-10-08 | Closed | Deploy user could not write /opt, ~/.docker owned by root; fixed on VM
| Backend CI / deploy red after merging #59, #61, #62 | Phone login fix and app review not on production | High | huynqbse180211 | 2026-10-12 | 2026-10-13 | Closed | Two order-service migrations both V23 + test without tempToken; fixed in backend #64
| SePay variables required before deploying SePay-only payment | Deploy stops at docker compose config | High | huynqbse180211 | 2026-10-13 | 2026-10-13 | Closed | SEPAY_* set on VM; backend deploys green from 13/10
| SMS / SMTP / Firebase keys not confirmed on VM | Receiver may not get SMS; email and push channels unverified | Medium | huynqbse180211 | 2026-09-16 |  | Open | APP_SMS_* (eSMS / Twilio), SPRING_MAIL_*, FIREBASE_CREDENTIALS_JSON
| Real drone flight not tested end-to-end | STANDARD drone orders depend on telemetry never tested in flight | High | nhatkse182290 | 2026-09-13 |  | Open | Telemetry + camera merged (iot 07/10, 21/10); bench-tested only, systemd on drone Pi not installed
| Physical cabinet CAB-TU01 wiring not finished | Cannot serve real parcels in the physical locker | Medium | huynqbse180211 | 2026-09-27 |  | Open | 7 boxes open from Pi; most door sensors not read; axis 2 needs a second TB6600
| Pi USB flash corrupted after power loss | Cabinet controller cannot boot / update | Medium | huynqbse180211 | 2026-09-26 | 2026-09-27 | Closed | Rebuilt Pi on 64 GB microSD
| Phone login matches only +84 format | Old accounts stored as 0... may get a duplicate account | Medium | huynqbse180211 | 2026-10-13 |  | Open | AuthService.firebaseLogin needs phone normalization
| Production data broken by rental bug before backend #20 | RENTAL orders completed early, unpaid orders, overdue rentals | Medium | binhtntse182370 | 2026-09-21 |  | Open | Data check queries not run yet
| GitHub Free plan: no branch protection | Review before merge only enforced by convention; several branches merged directly to main | Low | huynqbse180211 | 2026-09-13 |  | Open | See Q&A

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Locker Send | Send Parcel | binhtntse182370 | Confirm drop sends payment id instead of order id, so the drop is never confirmed | huynqbse180211 | Closed | mobile #19
Locker Rental | Rent Locker | binhtntse182370 | Rental order is COMPLETED when the customer reopens the box during the rental | huynqbse180211 | Closed | backend #20 hotfix
Customer | My Orders & Order Details | binhtntse182370 | All times shown 7 hours early; new orders immediately overdue (LocalDateTime parsed as local time) | huynqbse180211 | Closed | mobile #26
Admin | Promotions & Loyalty | binhtntse182370 | Promotion end time moves back 7 hours on every edit, codes expire by themselves | huynqbse180211 | Closed | frontend #19
Locker Rental | Rent Locker | binhtntse182370 | Extending a rental charges the already-paid amount again | huynqbse180211 | Closed | backend #26 (paid_amount)
Admin | Users List & User Details | binhtntse182370 | Create user wrongly reports duplicate email and leaves an orphan auth account | huynqbse180211 | Closed | backend #26, frontend #19
Admin | Notifications (Broadcast) | binhtntse182370 | Statistic cards always 0, totalPages fixed at 1, filters ignored | huynqbse180211 | Closed | frontend #19
Customer | Stores List & Store Details | binhtntse182370 | Directions button does nothing on Android 11+ | huynqbse180211 | Closed | mobile #26
Locker Rental | Overdue Fee | huynqbse180211 | EXPIRED rental cannot be completed after paying the overtime fee | binhtntse182370 | Closed | backend #42
Locker Send | Send Parcel | huynqbse180211 | Cancelling an unpaid order does not release the reserved box | binhtntse182370 | Closed | mobile #72, iot #18
Locker Technician | Technician Home (Tickets) | huynqbse180211 | Box ticket attached to CANCELED / COMPLETED order | binhtntse182370 | Closed | mobile #38
Customer | Locker Layout (Box Map) | huynqbse180211 | Locker grid overflows (RenderFlex) on small screens | binhtntse182370 | Closed | mobile #50
Admin | Lockers & Locker Layout | binhtntse182370 | Box map out of order; promotion create / edit returns 400; token refresh logs admin out | huynqbse180211 | Closed | backend #54, frontend #39
Admin | Admin Dashboard | binhtntse182370 | Realtime lost: duplicate CORS header on SockJS /ws | huynqbse180211 | Closed | backend #49
Common | Notifications | binhtntse182370 | Duplicate English notification '<type> event received' for every order / payment event | huynqbse180211 | Closed | backend #77
IoT | Cabinet Controller (GPIO + MQTT) | binhtntse182370 | Pi ignores backend open command (missing slotIndex, topic by locker name) | huynqbse180211 | Closed | iot #9, backend #33
Kiosk | Kiosk Rent & Drop | binhtntse182370 | Any voucher code shows 'applied' | huynqbse180211 | Closed | iot #19
Kiosk | Kiosk Rent & Drop | binhtntse182370 | Touch screen: no on-screen keyboard, home page overflows 1024x600 | huynqbse180211 | Closed | iot #10
Drone Delivery | Payment (SePay VietQR) | huynqbse180211 | Money arriving after a drone order is cancelled flips it to PAID and is never refunded | viltyse182544 | Closed | backend #52
Drone Delivery | Cancel / Flight Failure | huynqbse180211 | Refund of 0 VND still closes the order as REFUNDED | viltyse182544 | Closed | backend #52
Drone Delivery | Drone Booking | huynqbse180211 | Receive DRONE box could belong to another locker than the chosen receiver locker | viltyse182544 | Closed | backend #85
Common | Splash & Onboarding | huynqbse180211 | Mobile web build fails to compile | viltyse182544 | Closed | mobile #59
Payment | Payment (SePay VietQR) | binhtntse182370 | Locker order: wrong received amount recorded, paid order cancelled without refund, wallet can pay twice | huynqbse180211 | Closed | backend #82
Locker Send | Send Parcel | huynqbse180211 | PIN is not unique among active orders (no unique index) | viltyse182544 | Pending | F2-G10
IoT | Cabinet Controller (GPIO + MQTT) | binhtntse182370 | Most door sensors of CAB-TU01 are not read by the Pi | huynqbse180211 | Pending | Physical wiring

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
2026-09-13 | Which Git workflow and where is the source of truth for docs? | huynqbse180211 | Medium | Closed | GitHub Flow, main = production, merge = deploy (ADR-0001); central docs repo (ADR-0002)
2026-09-13 | Upgrade the org to GitHub Team to enforce review / branch protection? | huynqbse180211 | Low | Open | Free plan cannot enable rulesets; rule only enforced by PR template
2026-09-13 | Which SMS provider sends the pickup code to receivers without an account? | huynqbse180211 | Medium | Closed | Twilio trial first, then eSMS.vn (backend #73); sender can share code from app
2026-09-13 | Upgrade the SMS account to paid before going live? | huynqbse180211 | Medium | Open | Trial only sends to verified numbers
2026-09-13 | Which LLM and embedding for the RAG assistant? | huynqbse180211 | High | Closed | Claude + Voyage AI, separate pgvector container (ADR-0006)
2026-09-13 | Does the real drone talk to the backend by MAVLink or MQTT? | viltyse182544 | High | Closed | MAVLink autopilot <-> Pi on drone, MQTT Pi <-> order-service (drone telemetry contract)
2026-09-15 | Where to store images (avatar, ticket photos, store photos)? | huynqbse180211 | Medium | Closed | Cloudinary signed direct upload (ADR-0004)
2026-09-15 | Should business rules be hardcoded or configurable? | huynqbse180211 | High | Closed | Each service owns system_settings, edited on /admin/settings (ADR-0005)
2026-09-20 | How should a customer open the box at the real locker? | binhtntse182370 | Medium | Closed | Three ways: BLE proximity (one tap), QR scan, kiosk PIN
2026-09-27 | The cabinet ships without Arduino / RS485: how does the Pi control it? | huynqbse180211 | High | Closed | Pi drives relays and sensors by GPIO directly, RS485 kept as option (ADR-0007)
2026-09-27 | What MQTT topic / payload do backend and Pi agree on? | huynqbse180211 | High | Closed | cabinet/{lockerId}, open command with boxId + slotIndex = boxNumber - 1 (ADR-0008)
2026-10-07 | Cancelled order: refund to wallet or to bank account? | binhtntse182370 | Medium | Closed | REFUND_PENDING, admin transfers to the customer's bank account and attaches receipt
2026-10-09 | When is an unpaid order cancelled automatically? | binhtntse182370 | Medium | Closed | Configurable by admin (unpaid auto-cancel minutes), box released
2026-10-13 | Which payment methods are kept for go-live? | huynqbse180211 | High | Closed | Only SePay bank transfer (VietQR); MoMo, VNPay, cash removed
2026-10-20 | Dropped drone parcel: redeliver for free or refund compensation? | nhatkse182290 | Medium | Closed | Admin chooses free redelivery or compensation refund per incident policy